## Gantt Chart w % Complete (hidden)
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 5 | 2018-01-08 | 3 | 3 | 0 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 8 | 2018-01-11 | 3 | 2.4 | 0.6 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 11 | 2018-01-16 | 5 | 3 | 2 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 14 | 2018-01-19 | 5 | 2 | 3 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 17 | 2018-01-23 | 6 | 1.2 | 4.8 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 9 | 2018-01-12 | 3 | 3 | 0 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 12 | 2018-01-19 | 7 | 5.6 | 1.4 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 17 | 2018-01-19 | 2 | 1.2 | 0.8 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 22 | 2018-01-26 | 4 | 1.6 | 2.4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 15 | 2018-01-19 | 4 | 4 | 0 | Nathan | 100%
| Reserve Room | 2018-01-22 | 22 | 2018-01-23 | 1 | 0.8 | 0.2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 22 | 2018-01-26 | 4 | 2.4 | 1.6 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 26 | 2018-01-29 | 3 | 1.2 | 1.8 | Michael | 40%
| Create Invitations | 2018-01-22 | 22 | 2018-01-25 | 3 | 0.6 | 2.4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 15 | 2018-01-24 | 9 | 9 | 0 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 25 | 2018-01-30 | 5 | 4 | 1 | Meredith | 80%
| Update Messaging | 2018-01-24 | 24 | 2018-01-30 | 6 | 3.6 | 2.4 | Michael | 60%
| Publish Calculator | 2018-01-30 | 30 | 2018-01-31 | 1 | 0 | 1 | Rachel | 0%

## Carta Gantt
| TAREAS | INICIO | TERMINO | DIA DE INICIO | DIAS DE TRABAJO | PORCENTAJE COMPLETADO
Primer Mes (Incremento 1) - Admin, Login y Modelado BD
| Especificacion de Requisitos / Análisis | 2019-08-28 | 2019-09-04 | 0 | 7 | 100%
| Diseño | 2019-09-04 | 2019-09-11 | 7 | 7 | 95%
| Estudio de Frameworks | 2019-09-11 | 2019-09-27 | 14 | 16 | 80%
| Implementación | 2019-09-27 | 2019-10-04 | 30 | 7 | 66%
| Verificacion/Validacion | 2019-10-04 | 2019-10-10 | 37 | 6 | 0%
Segundo Mes (Incremento 2) - Implementacion BD y desarrollo funcionalidad del entrenador
| Especificacion de Requisitos / Análisis | 2019-10-10 | 2019-10-15 | 43 | 5 | 0%
| Diseño | 2019-10-15 | 2019-10-20 | 48 | 5 | 0%
| Implementación | 2019-10-20 | 2019-10-24 | 53 | 4 | 0%
| Verificacion/Validacion, Reunion con cliente | 2019-10-24 | 2019-10-30 | 57 | 6 | 0%
Tercer Mes (Incremento 3) - Desarrollo funcionalidad nutricionista
| Especificacion de Requisitos / Análisis | 2019-10-30 | 2019-11-02 | 63 | 3 | 0%
| Diseño | 2019-11-02 | 2019-11-09 | 66 | 7 | 0%
| Implementación | 2019-11-09 | 2019-11-17 | 73 | 8 | 0%
| Verificacion/Validacion, Reunion con cliente | 2019-11-17 | 2019-11-20 | 81 | 3 | 0%
Cuarto Mes (Incremento 4) - Desarrollo funcionalidad del cliente
| Especificacion de Requisitos / Análisis | 2019-11-20 | 2019-11-23 | 84 | 3 | 0%
| Diseño | 2019-11-23 | 2019-11-27 | 87 | 4 | 0%
| Implementación | 2019-11-27 | 2019-12-04 | 91 | 7 | 0%
| Verificacion/Validacion, Reunion con cliente | 2019-12-04 | 2019-12-08 | 98 | 4 | 0%
| Extension | 2019-12-08 | 2019-12-22 | 102 | 14 | 0%

## Manual Chart (hidden)
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 3 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 5 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 4 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 3 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 3 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 5 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 9 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 3 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 5 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 5 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 4 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 5 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 3 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 5 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 4 | Rachel | 40%